# Phase 2 Proposal – Operational Separation & Technical Migration

From: SBM Development Team

Prepared for: LSMK Corp. (주식회사 LSMK), Attn: Mr. Song Dong-jeong, CEO

Date: 2025-09-27

# 1. Executive Brief: Time, Cost & Benefits

• Duration: 8 weeks

• Goal: Refactor & modernize the stack (Express → NestJS, CRA → Next.js), improve modularity, and reduce technical debt. Operating BM and SBM as independent services is a natural outcome, ensuring scalability and risk reduction for the future.

• Effort estimate: 6.0 MM (3 × 2 months).

Expected Benefits

- 20–30% lower development cost for new features.

- 70–80% lower cross-impact risk (BM unaffected by SBM changes and vice versa).

- 20–30% faster release cycles for SBM features.

- Establish the technical foundation required for future feature development requested by LSMK (e.g., internal management, free trial, billing/e-invoice, reporting, multi-language & localization).

Cost Summary

| Option | Rate (USD/MM) | Effort | Estimated Cost (USD) |
| --- | --- | --- | --- |
| A – Monthly (Time & Material) | 1,700 | 6.0 MM | 10,200 |
| B – Per Phase (Fixed-Price) | 1,900 | 6.0 MM | 11,400 |

Notes: Option A bills actual effort monthly (capped at +30% over the initial estimate unless scope changes are agreed). Option B offers a fixed Phase 2 price based on 6.0 MM; significant scope changes will be handled via a Change Request (CR).

# 2. Scope & Deliverables

## Included

- Codebase quality improvement: resolve legacy issues, reduce technical debt, and ensure maintainability.

- Backend: split BM API & SBM API; Express → NestJS scaffolding; separate config/env and data schemas.

- Web: split BM Web & SBM Web; CRA → Next.js scaffolding; separate domains/subdomains.

- App: refactor and modernization of the mobile app codebase (iOS/Android).

- App Store / Google Play compliance: resolve existing warnings and ensure builds meet store review requirements.

- Data: separate DB schemas (bm.*, sbm.*); one‑time backfill of essential master data (companies, buildings, catalogs).

- Infra & Ops: two CI/CD pipelines; product‑tagged logging/metrics; rollback runbook; Nginx/SSL/subdomains.

## Out of Scope (handled as new phases/CRs)

- New business features (Phase 2 is foundation only).

- Full history data migration.

- Large UI/UX redesign beyond scaffolding.

- Third‑party integrations not specified at kick‑off.

# 3. Plan & Milestones (8 weeks)

| Weeks | Focus | Key Outputs |
| --- | --- | --- |
| 1–2 | Scaffold NestJS/Next.js; split runtimes; CI/CD; subdomains | SBM API/Web skeletons; pipelines running |
| 3–4 | Separate DB/S3/queues; partial backfill; logging/metrics | bm.* / sbm.* schemas; backfilled master data; tagged logs |
| 5–6 | Stabilization; internal UAT; rollback runbook | UAT complete; rollback procedures documented/tested |
| 7–8 | Hardening; documentation; handover | Go-live checklist; admin docs; sign-off |

# 4. Acceptance Criteria

- BM & SBM run independently; stopping SBM does not affect BM.

- API/Web have separate domains; logs/metrics/queues are isolated.

- One‑time backfill completed as agreed; BM data remains intact.

- Two CI/CD pipelines; standardized access/security; rollback runbook in place.

# 5. Commercial Terms

| Criteria | Option A – Monthly (Partner) | Option B – Per Phase (Fixed) |
| --- | --- | --- |
| Rates | 1,700/ 1,900 (standard) USD/MM | 1,900 USD/MM (fixed computation) |
| Billing | Monthly invoicing; full payment (no retention) | Per phase: 30% signing, 40% mid, 30% final |
| Warranty/Support | Preferential partner rates for long‑term maintenance; continuous monthly quality review | 30% of final payment retained until warranty ends (2w–1m) |
| Overrun | Billed by actual MM, capped at +30% of estimate unless CR agreed | Fixed at estimated MM; extra effort absorbed by us; major changes via CR |

# 6. Client Inputs Required

- Confirm data option: No migration / Partial backfill (recommended) / Full migration.

- Confirm subdomains for SBM API & Web.

# 7. Assumptions & Dependencies

- Initial deployment may share one EC2 (cost‑control); later scaling can be planned separately.

- Licenses or third‑party costs (if any) are excluded.