Phase 2 — Operational Separation & Technical Migration (a prerequisite before new features)

Date: 2025-09-25
From: SBM Development Team
To: LSMK / Dr. Song

## Executive Summary

Current status: BM is stable. SBM (Phase 1) currently reuses the same system as BM.

Problem with the shared setup: every change for SBM can affect BM, releases are slower, testing effort grows, and risks increase.

Our proposal in Phase 2: run BM and SBM as two separate services (API & WEB), without adding new features now.

How we implement (in short): we scaffold Next.js & NestJS (we do not rewrite), reuse existing business code, and port modules gradually (Auth/Users → Trials/Usage/Invoices).

Data decision needed:

• No migration — SBM starts fresh.

• Partial migration (recommended) — one‑time backfill of essential master data (e.g., companies, buildings, catalogs).

• Full migration — possible but requires more time & budget.

Estimated timeline: 8 weeks (Phase 2 only). We can start on one server to control cost.

Benefits: safer operations (BM unaffected by SBM), faster feature delivery later, easier maintenance and expansion.

What we need from you now: confirm the separation principle, select a data option above, and confirm subdomains for SBM.

## 1) Why we must stop the shared setup

If BM and SBM continue to share one codebase/runtime, total time and risk will increase: slower releases, heavier QA, harder maintenance, and possible impact on BM.

Cross‑impact risk: any change for SBM touches shared code and may unintentionally break BM.

Slower delivery & more QA: every SBM feature requires full BM regression → significant QA overhead.

Hard to refactor legacy safely: two product logics mixed with role/flag branches → refactoring becomes risky.

Diverging policies: trial/print/billing/i18n differences are error‑prone when kept in one system.

## 2) What “scaffolding Next.js & NestJS” means (we do NOT rewrite from scratch)

Build skeletons first: create clean NestJS and Next.js shells (routing, auth, i18n config, CI/CD, logging) so the new stack runs end‑to‑end early.

Reuse existing code: extract common business logic from current Express/React into shared TypeScript modules; NestJS/Next.js call these modules directly.

Strangler pattern, module by module: port low‑risk modules first (Auth/Users), then Trials/Usage/Invoices; keep BM (Express) and SBM (Nest) running in parallel and switch traffic once stable.

No big‑bang migration: BM keeps its runtime; SBM gets the new NestJS/Next.js runtime; both can live on one server initially.

Current challenges with the legacy architecture:

Mixed product logic: BM & SBM rules entangled behind roles/flags → growing complexity and hidden coupling.

Limited modular boundaries: hard to isolate deploy & testing per module; changes ripple through the codebase.

## 3) Scope & operating model (no new business features in Phase 2)

Backend (API): split into BM API & SBM API with separate config/env and separate data schemas; framework migration Express → NestJS.

Web: split into BM Web & SBM Web with separate domains/subdomains; framework migration CRA (React) → Next.js.

Mobile Apps: already separate; initially keep current API; later migrate the SBM app to the new SBM API when ready.

Infra & operations: start on a single EC2 with two processes; set up two CI/CD pipelines, product‑tagged logging/metrics, and a rollback runbook.

Data: separate DB schema (bm.*, sbm.*); one‑time backfill of essential master data; no full history migration in Phase 2.

Note: new business features will be delivered in subsequent phases after this foundation is in place.

## 4) Data — CLIENT CONFIRMATION REQUIRED (High Priority)

Please confirm one of the following options:

1) No migration: SBM starts with fresh data.

2) Partial migration (recommended): one‑time backfill of essential master data (e.g., companies, buildings, catalogs); large history stays in BM or is moved gradually.

3) Full migration: feasible but requires more time & budget; we will submit a dedicated plan if chosen.

## 5) Proposed timeline (8 weeks; Phase 2 only, no new features)

Weeks 1–2: Scaffold NestJS (SBM API) & Next.js (SBM Web); split runtimes (api-bm/api-sbm); CI/CD; Nginx/SSL/subdomains.

Weeks 3–4: Separate DB schemas, S3 prefixes, and queue/cron namespaces; one‑time backfill; product‑tagged logging/metrics; smoke tests.

Weeks 5–6: Stabilization, optimization, rollback runbook; internal UAT and (optional) client UAT.

Weeks 7–8: Fix follow‑ups, hardening, and documentation.

## 6) Acceptance criteria

BM & SBM operate independently; stopping SBM does not affect BM.

API/Web have separate domains; logs/metrics/queues are isolated.

One‑time backfill completed as agreed; BM data remains intact.

Two CI/CD pipelines; rollback runbook in place; access/security standardized.

## 7) Client confirmations required

Principle: approve Phase 2 (operational separation & technical migration).

Data: select **No / Partial (recommended) / Full** migration and specify datasets for partial backfill.

Domains: confirm subdomains for SBM API & Web

Best regards,
SBM Development Team